## Sheet1
Change Request ID | Change Request Description | Raised On | Raised By | Status | Type of Change | Effort Estimation | Assigned To | Scheduled Start Date | Scheduled End Date | Actual Start Date | Actual End Date | Final Status
CR-001 | Add multi-language support for onboarding forms | 2025-09-01 | Business Team | Open | Functional/UI | 40 hrs | Frontend Dev | 2025-09-10 | 2025-09-20 |  |  | Pending
CR-002 | Update KYC vendor API endpoint as per new compliance SLA | 2025-09-02 | Compliance Officer | In Progress | Integration/Regulatory | 24 hrs | Backend Dev | 2025-09-05 | 2025-09-07 | 2025-09-05 |  | Ongoing
CR-003 | Add escalation workflow in Ops Dashboard for SLA breaches | 2025-09-03 | Operations Manager | Open | Functional/Workflow | 32 hrs | Full-stack Dev | 2025-09-12 | 2025-09-18 |  |  | Pending
CR-004 | Enhance encryption algorithm to meet new GDPR guidelines | 2025-09-04 | Security Officer | Open | Non-Functional/Security | 50 hrs | Security Engineer | 2025-09-15 | 2025-09-25 |  |  | Pending
CR-005 | Add audit log export functionality for compliance review | 2025-09-05 | Compliance Officer | Closed | Functional/Reporting | 20 hrs | Backend Dev | 2025-08-20 | 2025-08-25 | 2025-08-20 | 2025-08-25 | Implemented